## Simple Business Risk Register
SIMPLE BUSINESS RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
GDPR risk due to unsecure data storage | Risk of being sued by customers/clients | 5 | 2 | 10 | Ensure we stick to regulations regarding data storage | Back-end team | 1
Zoom servers down | Would need to pay for alternative collaboration platform (i.e MS Teams) | 2 | 1 | 2 | Pay for alternative platforms in case, so that there is no time lost | Scrum-master | 2
Issues connecting to database | Would not have up to date customer/stock informaiton | 4 | 3 | 12 | Run several tests and only utilise reliable databases and data storage platforms | Back-end team | 3
Unable to display app properly on different platform (mobile, tablet etc) or different browsers | Poor customer experience | 2 | 3 | 6 | Create versatile front-end to adapt to different platforms (CSS media queries) | Front-end team | 4
Setting up database without Transactional annotation | RIsk of taking payment without performing customer order | 5 | 3 | 15 | Ensure we use Transactional annotations, and use TDD to ensure that the code is functioning appropriately | Back-end team | 5
Dependency may not be up to date | Certain components may not load appropriately, e.g. carousel component. | 3 | 3 | 9 | Ensure we use libraries that are regularly updated | Front-end team
Customers holding items in their basket in perpetuity | Items on the client may show 'out of stock' even though they have not been ordered | 4 | 3 | 12 | Have a timer to only hold items in a basket for a limited time | Front-end team
Payment fraud and identity theft | Users' details could be stolen, which would have large implications for their livelihoods, and would have legal implications for the company | 5 | 2 | 10 | Ensure user details are encrypted and stored securely | Back-end team

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.